## Progress Report
DEVELOPMENT PROGRESS REPORT (June 29 - July 15)
Developer Name: | Yudhveer
Reporting Period: | June 29, 2026 to July 15, 2026
Date Generated: | July 15, 2026
Date | Project | Component | Task Description & Activity Details | Status
2026-06-30 | ONBOARDING | Backend/Frontend | Initialized local workspace repository, configured environment structures, and mapped the core project layout for the Warehouse and Logistics Management System. | Completed
2026-07-02 | ONBOARDING | Backend/Database | Configured Docker containers for PostgreSQL database integration. Resolved migration dependencies and initialized superuser authentication settings. | Completed
2026-07-03 | ONBOARDING | Backend | Analyzed stock update concurrency logic using atomic Django F() expressions in serializers to prevent race conditions during inbound (GRN) and outbound (Dispatch) operations. | Completed
2026-07-03 | ONBOARDING | Frontend | Resolved zone code case-sensitivity bugs to display warehouse locations exactly as stored. Refined frontend dashboard layout elements. | Completed
2026-07-04 | BOI | Backend | Initial server repository configuration. Designed Django database models and configured API routes for core User and Booth management dashboards. | Completed
2026-07-07 | BOI | Frontend | Created front-end React boilerplate, integrated state managers, and customized branding templates with banking-themed styling guidelines. | Completed
2026-07-07 | ONBOARDING | Backend | Programmed custom 'IsAdminRole' API permissions. Implemented account soft-delete patterns, setting 'is_active=False' and 'employment_status=FORMER' to retain historical database references. | Completed
2026-07-07 | ONBOARDING | Frontend | Designed React User Management dashboard interface featuring real-time staff statistics cards, search filters, and account activation/deactivation dialogs. | Completed
2026-07-08 | BOI | Backend | Added dynamic loan amount parameters in product models. Established custom shared 'isAdminRegionalManager' REST permission controllers, configured database url endpoints, and set gitignore policies. | Completed
2026-07-08 | BOI | Frontend | Added dynamic fields for display of requested loan amounts in the products list view. Pushed first frontend build. | Completed
2026-07-08 | ONBOARDING | Backend/Security | Configured CustomTokenObtainPairSerializer to inject user roles and usernames into JWT token payloads. Compiled extensive architectural review documentation comparing DRF and Express.js paradigms. | Completed
2026-07-09 | BOI | Backend | Refactored user table, dropped redundant columns, pivoted booth/visitors logic to direct visitor log mapping, mapped product interest status metrics, and integrated database foreign relationships. | Completed
2026-07-09 | BOI | Frontend | Rebranded interfaces to 'Relationship Managers'. Implemented exit forms confirmation prompts, tabbed product structures with view persistence, and user analytics statistics dashboard charts. | Completed
2026-07-09 | SAKHI | Frontend | Completed deployment of updated dashboard website structure, initial layout, and core routing structure. | Completed
2026-07-10 | BOI | Backend | Built onsite tracking statistics APIs, designed custom WhatsApp message rate throttling rules, and debugged URL redirection issues. | Completed
2026-07-10 | BOI | Frontend | Resolved demographics analytics dashboard chart display bugs. | Completed
2026-07-10 | SAKHI | Backend | Created 'is_tester' database flags. Programmed secure 2FA authentication, SMTP configuration, and verification endpoints in Django backend. | Completed
2026-07-10 | SAKHI | Frontend | Integrated 2FA OTP verification screens, email delivery timers, and input validation components. | Completed
2026-07-13 | BOI | Backend | Configured global server-side API request timeout handlers for server resilience. | Completed
2026-07-14 | SAKHI | Backend | Modified location database models and updated 2FA login views. | Completed
2026-07-14 | SAKHI | Frontend | Refactored global tables to flex layouts ('height=flex'), preventing scrollbar duplicate issues. Programmed right-aligned numeric pagination text-inputs ('Page [ X ] of Y') globally. Removed mock data config and reconnected backend APIs. | Completed
2026-07-15 | BOI | Backend | Synced and merged master branch code with local features on dev branch ('yudhveer_dev'). | Completed
2026-07-15 | ONBOARDING | Backend/Security | Configured Django CORS middleware settings to resolve cross-origin API communication errors between the React frontend and Django backend. | Completed
2026-07-15 | SAKHI | Frontend | Converted all table buttons (Approve, Reject, Call, Feedback, Edit, Delete) to clean icon-only buttons with hover tooltips. Fixed unimported 'Eye' icon, cascading close-panel states, and resolved a white-screen crash on the Geographical Referrals tab. | Completed
2026-07-15 | SAKHI | Frontend/Security | Fixed JWT session timeout crash by enabling rotated refresh token saving (SimpleJWT rotation) in axios response interceptors and rebinding auto-logout timer to the refresh token (7 days) instead of the access token (1 hour). | Completed
SUMMARY OF TASK METRICS
Total Sakhi Tasks Completed:
Total BOI Tasks Completed:
Total Onboarding Tasks Completed:
Overall Combined Tasks: